## Tabellenblatt1
Week | 3.-9. Feb | 10.-16. Feb | 17.-23. Feb | 24. Feb-2. Mar | 3.-9. Mar | 10.-16. Mar | 17.-23. Mar | 24.-30. Mar | 31. Mar-4. Apr (Final Week)
Task
Project Initialization | Team Assembly, First Meeting
Data Acquisition |  | Sighting of EU/French Data, Teamwork try with Google Colab
Data Preprocessing |  | Handling of NaNs, encoding errors, etc.
Exploratory Data Analysis |  | Reducing Explanatory Vars, Corr Tables, Relevance Analysis... | Splitting up into Electric & Combustion
Architecture |  |  | Setup of Preprocessing Pipeline, Pre-Commit Hooks...
Reports |  |  | Sighting of Report Guidelines & First Texts | Finalised Report 1: Preprocessing |  |  |  | Finalised Report 2: Modeling | Finalised Report 3: Conclusion
ML Model Development |  |  |  |  | Discussion on Modeling Approach, Distribution of who does which models | Joint Start, Lazy Regressor and Basic Models | Focus on Tree Models
ML Model Refinement & Advanced Techniques | [6 empty] | Bagging, Interpretability Methods
Deep Learning Models | [7 empty] | Classification: Keras. Regression: Neural Nets
Model Evaluation | [7 empty] | Evaluation of the best Models
Presentation | [8 empty] | Streamlit Lessons, First Discussion & Drafts